BỘ GIÁO DỤC VÀ ĐÀO TẠO TRƯỜNG ĐẠI HỌC VĂN LANG KHOA KỸ THUẬT CƠ ĐIỆN VÀ MÁY TÍNH CAPSTONE PROJECT – GROUP 15 Design and Development of a Simulation-Based Game Application for Fire Prevention and Firefighting Training Major: Software Engineering Document: PROJECT PLAN Version: 1.2 ¦ Date created: January 1st, 2026 Group Student: BÙI LÊ ĐỨC HUY*; 2274801030183. BÙI LÊ ĐỨC HIẾU; 2274801030046. LÊ TUẤN ANH; 2274801030228. Mentor: Ths. Lã Hoàng Quý Hồ Chí Minh City – January 1st, 2026

# REVISION HISTORY

| Project Information Overview |  |  |
| --- | --- | --- |
| Project Title | Design and Development of a Simulation-Based Game Application for Fire Prevention and Firefighting Training |  |
| Product Name | Ignis Guard |  |
| Project Mentor | Ths. Lã Hoàng Quý |  |
| Partner Organization | No external partner organization |  |
| Team members | Bùi Lê Đức Huy* | 2274801030183 |
|  | Bùi Lê Đức Hiếu | 2274801030046 |
|  | Lê Tuấn Anh | 2274801030228 |

| Document Information |  |  |
| --- | --- | --- |
| Document Title | PROJECT PLAN |  |
| Author(s), Role(s) | Bùi Lê Đức Huy | Team Leader, Unity Programmer, Game Designer, 3D Artist |
|  | Bùi Lê Đức Hiếu | Unity Programmer, Game Designer, UI/UX Designer, Writer/Content |
|  | Lê Tuấn Anh | Writer/Content, QA, Game Designer |
| Changelog | 1/1/2026 – v1.0 | Initial version of the Project Plan created and baselined for Group 15. |
|  | 8/3/2026 – v1.1 | Updated scope, target users, tool stack, and selected planning details for consistency. |
|  | 8/3/2026 – v1.2 | Added SPQP alignment, documentation updates, and final consistency refinements. |

# TABLE OF CONTENTS

REVISION HISTORY	2

TABLE OF CONTENTS	3

LIST OF FIGURES	7

LIST OF TABLES	8

Chapter 1.	Project Overview	9

1.1	Project title	9

1.2	Background & problem statement	9

1.3	Project description	9

1.4	Project vision	10

1.5	Stakeholders & target users	10

1.6	Deliverables	11

1.7	Success metrics	12

Chapter 2.	Scope and Objectives	13

2.1	Project objectives (education + technical)	13

2.1.1	Educational Objectives	13

2.1.2	Technical Objectives	13

2.2	In-scope	13

2.3	Out-of-scope	14

2.4	Assumptions & constraints	14

2.5	Scope baseline & traceability	15

Chapter 3.	Product Plan and Prioritization	16

3.1	Product backlog overview (theo module)	16

3.2	Prioritization (MoSCoW: Must/Should/Could/Won’t)	16

3.3	MVP definition (Vertical Slice / Minimum Demo)	17

3.4	Definition of Done (DoD)	17

3.5	Quality gates	18

Chapter 4.	Work Plan	19

4.1	Development methodology	19

4.2	Work Breakdown Structure (WBS)	19

4.3	Schedule / Timeline	20

4.4	Milestones (M1/M2/M3…) & acceptance criteria	26

4.5	Task assignment / responsibility	28

Chapter 5.	Technical Approach Summary	29

5.1	High-level architecture overview	29

5.2	Key technical decisions (ví dụ: data-driven scenarios, deterministic mapping)	29

5.2.1	Data-Driven Scenario System	29

5.2.2	Deterministic Parameter Mapping	29

5.2.3	Mission Tree & Trigger System	30

5.3	Dependencies (Unity packages, assets, tools)	30

5.4	Technical risks & mitigation (ngắn gọn)	30

Chapter 6.	Resource Management	31

6.1	Team structure & roles	31

6.2	Tools & technology stack (Unity version, repo, CI nếu có)	31

6.3	Resource plan	32

6.3.1	Hardware Requirements	32

6.3.2	Asset Sourcing	32

6.3.3	Time Allocation	32

Chapter 7.	Risk Management	33

7.1	Risk management approach	33

7.2	Risk register	33

7.3	Mitigation & contingency	34

7.4	Risk Ownership	35

Chapter 8.	Progress Monitoring and Reporting	36

8.1	Tracking metrics (burndown/checklist/bug count/playtest notes)	36

8.2	Reporting cadence (weekly: done/next/blockers)	36

8.3	Artifact management (versioning docs, build naming, storage)	37

8.3.1	Version Control (Source Code)	37

8.3.2	Build Naming & Versioning	37

8.3.3	Documentation & Asset Storage	37

Chapter 9.	Change Management	38

9.1	Change request process	38

9.2	Scope control rules (chống scope creep)	38

Chapter 10.	Test & Validation Plan Summary	40

10.1	Test strategy overview (unit/integration/playmode)	40

10.2	Validation against SRS (FR/NFR coverage)	40

10.2.1	Functional Requirements (FR) Validation	40

10.2.2	Non-Functional Requirements (NFR) Validation	41

10.3	Demo checklist	41

Chapter 11.	Lessons Learned & Recommendations	42

11.1	Lessons learned	42

11.2	Recommendations / future work	42

11.2.1	Technical Enhancements	42

11.2.2	Content Expansion	43

11.2.3	Educational Integration	43

CONCLUSION	44

REFERENCES	45

# LIST OF FIGURES

Figure 4.1 SCRUM Process	20

# LIST OF TABLES

Table 3.1 Overview of System Modules and Features	17

Table 3.2 Development Milestones and Acceptance Criteria	19

Table 4.1 Project Sprint Plan	22

Table 4.2 Project Milestones and Acceptance Criteria by Sprint	27

Table 5.1 Dependencies Used in the Project	31

Table 5.2 Project Technical Risks and Mitigation Measures	31

Table 6.1 Development Tools and Software Used in the Project	32

Table 7.1 Risk Register for the Project	34

Table 8.1 Project Reporting Plan	37

Table 10.1 Demo Checklist by Milestone	42

# Project Overview

## Project title

Formal Title: Design and Development of a Simulation-Based Game Application for Fire Prevention and Firefighting Training.

Product Name: Ignis Guard.

## Background & problem statement

Background: Firefighting and Rescue (FFR) operations demand extreme precision, rapid decision-making, and strict adherence to safety protocols. Traditional training methods often face significant barriers, including high operational costs, inherent safety risks to trainees, and the difficulty of replicating complex, high-stakes fire scenarios. Consequently, Serious Games have emerged as a vital tool in modern pedagogy, providing a risk-free environment for professional skill acquisition.

Problem Statement: Most existing firefighting simulations focus primarily on the physical "On-site" actions (e.g., spraying water) while neglecting the critical "Call Phase"—the stage where initial information is gathered. Inaccurate assessment of the situation during a 911 call often leads to fatal tactical errors and improper resource allocation. Furthermore, many current simulations utilize static environments, which encourage rote memorization rather than the adaptive, variable-based thinking required in real-life emergencies.

## Project description

This project involves the design and development of Ignis Guard, a simulation-based serious game built with the Unity engine for fire-response and firefighting training. The game is developed as a single-player 3D first-person training experience in which the player must assess an emergency situation, make informed tactical decisions, and execute on-site firefighting procedures in accordance with supervisor-approved SOP principles.

The project is structured around one shared educational gameplay loop deployed across two playable scenarios. In the Call Phase, the player participates in a timed, dialogue-based emergency-call interaction and selects questions to gather critical information from the caller. The collected answers are then processed by an Incident State logic layer, which converts the call results into deterministic scenario parameters such as fire intensity, smoke conditions, hazard presence, and victim-related variables.

These parameters are then applied to the selected scenario before the player enters the field. In the On-site Phase, the player assumes the role of a fire-response leader and must carry out key mission objectives such as scene assessment, hazard handling, victim rescue, and fire suppression using basic tools and scripted teammate support. After mission completion, the game provides a Result/Debrief screen that evaluates performance based on safety, efficiency, mission success, and SOP compliance, while also explaining the cause-and-effect relationship between earlier call decisions and later on-site outcomes.

As a capstone-scale implementation, the project focuses on delivering one polished MVP scenario together with a second fully playable scenario built on the same data-driven architecture. This scope demonstrates the project’s core thesis contribution: an educational training loop in which information gathered before deployment directly and visibly affects operational conditions, while also proving that the underlying system can scale beyond a single scenario.

## Project vision

The project aims to provide a flexible digital training platform that fosters systemic thinking. By bridging the gap between theoretical SOP knowledge and real-world tactical reflexes, Ignis Guard seeks to become a comprehensive tool for fire safety education where every decision has a visible, logical consequence.

## Stakeholders & target users

Stakeholders:

- Project Supervisor: Oversees technical quality, academic rigor, and alignment with the capstone requirements.

- Thesis Defense Committee: Evaluates the project’s feasibility, implementation quality, educational relevance, and innovation.

- Development Team (Group 15): Responsible for design, programming, content creation, testing, and documentation throughout the 20-week project lifecycle.

Target Users:

- Primary Target Users - FFR Trainees: Recruits and students who need to practice situational assessment, emergency-call information gathering, and SOP-based response planning in a controlled training scenario.

- Secondary / Future Expansion Users - Industrial Safety Officers: Personnel responsible for workplace fire safety training who may benefit from later scenario extensions tailored to industrial environments.

- Secondary / Future Expansion Users - Educational Institutions: Schools or organizations seeking serious-game-based learning tools for fire safety awareness and introductory emergency response education.

## Deliverables

The final project submission will include the following deliverables:

1. Software Build

A fully functional Windows executable build of Ignis Guard, including two playable scenarios built on the same core gameplay loop.

2. Source Code Package

The complete Unity project source code, including scripts, scenes, configuration files, and project assets required to reproduce the final build.

3. Documentation Suite

- Project Charter

- Project Plan

- Software Process and Quality Plan (SPQP)

- Software Requirements Specification (SRS)

- Software Design Description / Software Architecture Design (SDD)

- Test Report

- Evaluation Report

- User Manual

- Final Thesis Report

4. Supporting Submission Materials

- Demo Video

- README / installation and deployment instructions

- Asset attribution list, where applicable

## Success metrics

The project’s success will be measured by the following criteria:

Technical Performance:

The target performance is an average of 60 FPS during normal gameplay, with a minimum acceptable threshold of 30 FPS under test conditions, and no critical game-breaking bugs in the core gameplay loop.

Target Test Hardware:

Intel Core i5-11th gen (or equivalent), 8 GB RAM, NVIDIA GeForce RTX 3050 Laptop GPU 6 GB VRAM (or equivalent), Windows 11, Full HD resolution.

Parametric Accuracy:

The system must demonstrate correct and deterministic mapping between Call Phase inputs and On-site environmental changes. The same input set must consistently generate the same Incident State and scenario outcome.

Educational Impact:

During playtesting and evaluation, users should be able to identify at least 80% of their major tactical mistakes through the debriefing system.

SOP Alignment:

The mission structure, task order, and safety priorities must reflect the intended training logic and supervisor-approved firefighting SOP principles.

# Scope and Objectives

## Project objectives (education + technical)

The objectives are divided into two primary categories to satisfy both the educational purpose of the "Serious Game" and the technical requirements of a Computer Science thesis.

### Educational Objectives

Protocol Mastery: To train users on the Standard Operating Procedures (SOP) for fire response, emphasizing the "Safety First" principle.

Information Synthesis: To develop the user’s ability to extract critical data during emergency calls and understand how that data dictates tactical decisions.

Consequence Awareness: To provide a feedback loop where players observe the direct impact of their choices (e.g., failing to identify a gas leak leads to an explosion on-site).

### Technical Objectives

Dynamic Scene Parameterization: To implement a system that modifies 3D environment variables (fire, smoke, hazards) in real-time based on external data inputs (Call Phase results).

Mission Tree Architecture: To develop a robust, prerequisite-based mission system that tracks player progress and validates objective completion.

AI Command System: To create a simplified command interface for non-player character (NPC) teammates to perform basic tasks (e.g., "Secure Area" or "Break Door").

## In-scope

The project will focus on the following core modules and features:

- Core Game Loop: Complete flow from Main Menu / Scenario Start → Call Phase → On-site Operation → Result/Debrief.

- Call Phase Minigame: A time-constrained UI-based interaction for information gathering.

- Incident State Mapping: A logic layer that translates Q&A answers into scene parameters (Hazards: Gas/Electric/Smoke; Victims: Count/Location).

- On-site Mechanics: First-person movement, interaction with firefighting tools, and victim rescue.

- Squad Commands: A basic command system to assign simple tasks to a bot teammate.

- Evaluation System: A grading algorithm (C to S rank) based on time, SOP compliance, and safety metrics.

- Scenario Coverage: Two playable scenarios implemented on the same shared architecture, each with its own mission configuration, hazard arrangement, and environmental context.

- Scenario Selection / Loading: The system must support selecting and loading the approved scenario configuration before gameplay begins.

## Out-of-scope

To ensure project feasibility within the capstone timeline, the following are excluded:

- Advanced Fluid Dynamics: Fire and water will be represented using particle systems and shaders rather than high-fidelity, real-time physical fluid simulations.

- Multiplayer/Networking: The game is strictly single-player.

- Open World: The game is scenario-based; players cannot move outside the designated mission boundaries.

- Vehicle Simulation: Driving the fire truck to the scene is not included; the game starts at the call and then "teleports" the player to the site.

- Character Customization: Player and bot appearances will be pre-defined.

## Assumptions & constraints

Assumptions:

- Users have basic familiarity with first-person navigation (WASD + Mouse).

- The provided 3D assets (models/animations) are compatible with the selected Unity version.

Constraints:

- Time: The project is planned over 20 weeks, divided into 10 sprints, with each sprint lasting 2 weeks.

- Platform: The game is developed for PC Windows only. VR, mobile, and console support are out of scope.

- Resources: Development is carried out by a 3-member student team using Unity 6.0, asset-store/prototype assets, and a limited academic project budget.

- AI Scope: Teammate AI is intentionally limited to simple scripted commands rather than advanced autonomous squad behavior.

## Scope baseline & traceability

The scope is baselined against the Software Requirement Specification (SRS). Every feature implemented in the Work Plan (Chapter 4) must be traceable back to the objectives defined in section 2.1.

- Traceability Matrix: A document will be maintained to map each gameplay mechanic to its corresponding educational goal (e.g., the "Gas Hazard" parameter maps to the "Hazard Recognition" learning objective).

- Change Control: Any additions to the In-scope list must undergo a formal impact assessment as detailed in Chapter 9.

# Product Plan and Prioritization

## Product backlog overview (theo module)

The project is divided into five core modules. Each module contains specific features required to complete the "Call-to-Debrief" loop.

Table 3.1 Overview of System Modules and Features

| Module | Features |
| --- | --- |
| M1: Core System | Level Manager, Game State Controller (Global State), Scenario Loader and Session State Persistence. |
| M2: Call Phase | Q&A UI, Timer logic, Data mapping (Logic to convert answers to IncidentState). |
| M3: Environment | Scenario maps, Fire/Smoke particle systems, Hazard triggers (Gas/Electric), Victim spawning. |
| M4: Gameplay | FPS Controller, Interaction system, Fire extinguisher mechanics, Squad (Bot) AI tasks. |
| M5: Evaluation | Scoring algorithm, Rank UI (C to S), Cause-and-Effect debriefing text generator. |

## Prioritization (MoSCoW: Must/Should/Could/Won’t)

To manage the development timeline effectively, features are prioritized using the MoSCoW method based on the approved two-scenario project scope.

Must Have (Critical for baseline scope):

- Functional Call Phase with at least 3 critical questions.

- Dynamic parameterization (Call Phase inputs changing On-site fire/hazard intensity).

- Basic On-site movement and firefighting interaction.

- Mission system (e.g., rescue victim, extinguish fire, complete required objectives).

- Basic Result screen with C-S ranking.

- Two playable scenarios built on the same core architecture, with one designated as the primary MVP validation scenario.

Should Have (Important but not vital for the first integrated demo):

- Squad command system (assigning 1-2 simple tasks to a bot).

- Multiple hazard types (e.g., Electricity and Gas).

- Detailed cause-and-effect debriefing feedback.

- Scenario-specific mission variations and objective flow refinement.

Could Have (Desirable if time permits):

- Advanced visual effects (volumetric smoke, heat haze).

- Mini-map or navigation compass.

- Additional environmental polish and secondary non-critical interactions.

Won’t Have (Out of current scope):

- Online Multiplayer.

- Driving simulation / vehicle physics.

- Open-ended NLP-based emergency-call dialogue.

## MVP definition (Vertical Slice / Minimum Demo)

The Minimum Viable Product (MVP) for this thesis is defined as one polished end-to-end scenario that validates the shared system architecture, while the final project scope includes two playable scenarios.

- MVP Baseline: One primary scenario is polished to the level required for milestone validation, internal playtesting, and thesis demonstration readiness.

- Secondary Scenario: A second scenario is implemented on the same core gameplay loop, using shared systems for the Call Phase, Incident State mapping, mission flow, and Result/Debrief evaluation, while containing its own scenario-specific content.

- The Flow: The player completes the Call Phase, enters the selected on-site environment where fire and hazard conditions are determined by call performance, executes mission objectives, and receives a final grade with educational feedback.

- Goal: To prove that the data-driven scenario pipeline (Call Phase → Incident State → On-site → Debrief) works reliably, and that the architecture is reusable across more than one scenario without redesigning the core system.

## Definition of Done (DoD)

A feature is considered "Done" only when it meets the following criteria:

- Functionality: The feature works according to the requirements in the SRS.

- Integration: The feature is integrated into the main Unity branch without breaking existing systems.

- Stability: No critical bugs or "null reference" errors occur during playtests.

- Performance: The feature does not cause frame rate drops below 30 FPS.

- Documentation: Code is commented, and any new assets are properly named and organized in the project folder.

## Quality gates

The project must pass through specific quality checkpoints at each milestone:

Table 3.2 Development Milestones and Acceptance Criteria

| Milestone | Quality Gate Criteria |
| --- | --- |
| M1: Prototype | Core movement and Call Phase UI logic are functional in a "Greybox" environment. |
| M2: Alpha | Parameterization logic is fully linked; the game loop is playable from start to finish. |
| M3: Beta | All "Must-Have" and "Should-Have" features are implemented; assets/VFX are polished. |
| M4: Final | Bug-free (zero High/Critical bugs); scoring system is balanced for educational use. |

# Work Plan

## Development methodology

The project follows the Scrum framework to ensure iterative progress and flexibility.

- Sprint Duration: 2 weeks.

- Sprint Planning: Held at the start of each sprint to define the Sprint Goal and select items from the Product Backlog.

- Daily Stand-up: Short daily syncs to discuss progress and blockers.

- Sprint Review & Retrospective: Held at the end of each sprint to demo functional increments and improve the development process.

- The detailed lifecycle phases, phase-specific activities, quality control procedures, verification and validation approach, and corrective-action rules are defined in the companion Software Process and Quality Plan (SPQP). This Project Plan remains the governing baseline for scope, schedule, resources, risk management, and reporting.

Figure 4.1 SCRUM Process

## Work Breakdown Structure (WBS)

The project is broken down into the following functional work packages:

WP1: Project Foundation & Planning

- SRS & SDD Documentation.

- Core Loop Architecture (State Machine).

- Basic UI Framework (Level Select).

WP2: Call Phase Module

- Timed Q&A UI System.

- Question/Answer Data Structure (JSON/Scriptable Objects).

- Parameter Calculation Logic (Incident State generator).

WP3: Environment & On-site Simulation

- Map Design (Modular Environment).

- Parameterized Hazard Spawning (Fire, Smoke, Gas, Electricity).

- Victim Placement & Randomization Logic.

WP4: Gameplay Mechanics

- FPS Controller & Interaction System.

- Fire Tool (Extinguisher) Mechanics.

- Squad Command System (Bot AI for simple tasks).

WP5: Mission & Evaluation

- Mission Tree System (Prerequisites & Triggers).

- Scoring Algorithm (C to S Rank).

- Educational Debrief System (Cause-and-Effect feedback).

WP6: Thesis Finalization

- Final Bug Fixing & Optimization.

- Complete Thesis Report.

## Schedule / Timeline

The project is planned over 10 sprints, with each sprint lasting 2 weeks, for a total development timeline of 20 weeks. The team aims to deliver a 3D single-player serious game, Ignis Guard, on PC Windows with two playable scenarios built on one shared gameplay architecture. The development process begins with scope definition, two-scenario planning, and system architecture design, followed by implementation of the Call Phase, Incident State system, On-site gameplay, teammate command system, scoring, and debriefing features. The first half of the schedule focuses on establishing and validating the common gameplay loop through one MVP scenario, while the later sprints extend, integrate, test, and polish the second scenario using the same core framework. The final sprints focus on quality assurance, educational evaluation, cross-scenario validation, polishing, and preparation of all project deliverables, including source code, playable build, technical documents, report, slides, and demo video.

Table 4.1 Project Sprint Plan

| Sprint | Goal | Detailed Tasks | Assigned Members | Deliverables |
| --- | --- | --- | --- | --- |
| Sprint 1 | Project initiation and two-scenario scope definition | Define project vision, learning objectives, and project baseline; confirm the two approved scenarios and identify one as the MVP validation scenario; define the shared gameplay loop (Call Phase → Incident State → Preparation → On-site → Result/Debrief); set up Unity project, repository, Git workflow, folder structure, and naming conventions; draft initial backlog; prepare initial outlines for GDD, SRS, and risk list. | Huy: Unity project setup, repo, technical baseline. Hieu: gameplay loop draft, UI flow draft, initial GDD/SRS structure. Tuấn Anh: scenario concept, learning goals, initial risk list. | Project scope baseline; approved two-scenario concept; designated MVP scenario; product backlog v1; Unity project/repository setup; GDD outline; SRS outline; initial risk register. |
| Sprint 2 | Pre-production design and architecture for two scenarios | Finalize detailed design for both scenarios; define caller background, hazards, victim hints, and win/fail conditions for each scenario; design the rule-based branching dialogue tree; define shared Incident State parameters and scenario-specific rule mappings; design mission tree and scoring rubric; prepare architecture design, architecture drivers, and UI wireframes. | Huy: system architecture, data model design, technical feasibility. Hieu: UI wireframes, dialogue structure, SRS/GDD development. Tuấn Anh: scenario writing, SOP mapping, scoring/debrief content draft. | Two-scenario design specification; dialogue tree specification; Incident State model specification; mission/scoring specification; software architecture draft; UI wireframes. |
| Sprint 3 | Core framework and Call Phase prototype | Implement scene/game flow controller; create data structures for scenario, dialogue, Incident State, missions, and scoring; build Call Phase prototype with timer/turn limit and question-answer tracking; implement rule-based branching logic; create prototype Incident State calculator and equipment recommendation logic; create Call Phase UI prototype; run initial functional tests. | Huy: core architecture code, state flow, data systems. Hieu: Call Phase UI, dialogue implementation, content hookup. Tuấn Anh: dialogue content refinement, test checklist for Call Phase. | Playable Call Phase prototype; Incident State calculation prototype; equipment recommendation prototype; updated technical notes. |
| Sprint 4 | On-site gameplay foundation | Implement FPS movement and look controls; build interaction system (doors, switches, hotspots, simple object use); create blockout scenes for the approved scenarios; place hazards, triggers, and possible victim locations; create prototype tools (e.g., extinguisher, flashlight); build basic fire/smoke placeholders; create mission tracker prototype and HUD. | Huy: FPS controller, interaction system, scene blockout, triggers. Hieu: HUD/UI, tool interaction support, objective display. Tuấn Anh: objective content logic, on-site test case drafting. | On-site prototype framework; scenario blockout scenes; FPS movement and interaction system; tool use prototype; objective tracker prototype. |
| Sprint 5 | Incident-driven scene adaptation and teammate command system | Implement mapping from Incident State parameters to scene changes; enable/disable hazards based on call information; adjust smoke/fire levels and victim hint placement; create equipment recommendation briefing screen; implement simple scripted teammate commands (follow, wait, inspect, assist); connect bot actions to selected tasks; test the Call-to-On-site data pipeline across both scenario configurations. | Huy: scene adaptation system, bot logic, trigger integration. Hieu: command UI, preparation/briefing UI, data hookup. Tuấn Anh: validation of rule tables, QA matrix for scenario variants. | Working scene adaptation system; equipment recommendation screen; teammate command prototype; end-to-end data pipeline prototype; scenario rule tables for both scenarios. |
| Sprint 6 | Full gameplay loop integration for MVP scenario and reusable scenario framework | Integrate main menu, Call Phase, preparation, On-site Phase, and Result/Debrief into one complete loop; implement mission tree logic and success/failure rules; implement scoring calculation and rank mapping (C–S); create debrief logic with cause-effect educational feedback; complete first full integration on the MVP scenario; integrate the second scenario into the shared loading/configuration framework; conduct first internal playtest; update design/architecture documents to match implementation. | Huy: mission/scoring backend, overall integration. Hieu: result/debrief UI, scene flow polish, content linkage. Tuấn Anh: debrief content, playtest notes, bug logging. | End-to-end MVP scenario alpha; reusable scenario-loading/configuration framework; scoring/ranking system; debrief prototype; internal playtest report; updated GDD/SRS/architecture docs. |
| Sprint 7 | Content completion for both approved scenarios | Finalize scenario content, dialogue, mission triggers, victim logic, and hazard presentation for both approved scenarios; improve tool usage feedback; improve teammate command usability; polish environments using asset store/prototype assets; improve audio placeholders; conduct second internal playtest focused on clarity, pacing, learning value, and cross-scenario consistency. | Huy: scene polish, gameplay feel, technical fixes. Hieu: UI polish, content integration, feedback improvements. Tuấn Anh: final writing, rubric refinement, regression QA. | Content-complete beta build with two playable scenarios; refined scenario scripts; improved mission/debrief content; playtest round 2 report. |
| Sprint 8 | QA, balancing, and evaluation preparation | Create formal Test Plan and detailed test cases; perform functional, integration, and UX testing; test Call branches, Incident mapping, mission progression, score/rank correctness, and bot commands across both scenarios; fix high-priority and medium-priority bugs; balance timer limits, mission pacing, and score thresholds; prepare educational/usability evaluation method and questionnaires. | Huy: gameplay/system bug fixing, balancing. Hieu: UI/UX fixes, score/debrief refinement, test support. Tuấn Anh: test documentation, QA execution, evaluation instruments. | Test Plan; test cases; bug list and fix log; evaluation plan; balanced beta build validated across both scenarios. |
| Sprint 9 | User evaluation and documentation consolidation | Conduct small-scale user evaluation; collect feedback on usability, perceived learning value, gameplay clarity, and debrief usefulness across the implemented scenarios; analyze evaluation results; implement major fixes from user feedback; finalize GDD, SRS, architecture document, Test Report, Evaluation Report draft; prepare thesis/report draft, slide outline, and demo script. | Huy: technical stabilization, architecture input finalization. Hieu: report drafting, slide structure, UI polish. Tuấn Anh: evaluation execution, data analysis summary, QA regression, report support. | Evaluation summary; near-final two-scenario build; finalized technical documents; thesis/report draft; demo script. |
| Sprint 10 | Final polish, packaging, and delivery | Perform final bug fixing and optimization pass; finalize UI/UX polish and balancing; create Windows release build; clean and organize source code; prepare README, install guide, and asset attribution; finalize thesis/report, demo video, screenshots, and appendix materials; rehearse final demo and defense presentation. | Huy: final build, source cleanup, performance fixes. Hieu: final UI polish, slide/demo support, packaging documentation. Tuấn Anh: final QA pass, proofreading, rehearsal notes. | Final Windows build with two playable scenarios; source code package; final thesis/report; demo video; final Test Report; final Evaluation Report; release/readme package. |

## Milestones (M1/M2/M3…) & acceptance criteria

Table 4.2 Project Milestones and Acceptance Criteria by Sprint

| Milestone | Sprint | Description | Acceptance Criteria |
| --- | --- | --- | --- |
| M1 | 1 | Project scope, approved scenarios, and setup completed | - Two approved scenarios are identified and documented. - One scenario is designated as the MVP validation scenario. - The baseline project scope is approved by the team and supervisor. - Unity project, repository, folder structure, and backlog are initialized. - Initial GDD and SRS outlines are completed. |
| M2 | 2 | Two-scenario design, architecture, and documentation foundation completed | - Design specifications for both scenarios are completed. - The Call Phase dialogue tree is documented. - Shared Incident State parameters and scenario rule mappings are finalized. - Architecture draft and UI wireframes are completed. |
| M3 | 3 | Call Phase prototype completed | - The Call Phase can run with a timer or turn limit. - The player can select questions and receive rule-based responses. - Answers are stored correctly. - A prototype Incident State output is generated from the call data. |
| M4 | 4 | On-site gameplay prototype completed | - First-person movement and camera control function correctly. - The player can interact with at least core environmental objects. - At least one firefighting tool prototype is usable. - HUD and mission tracker prototype are visible and functional. |
| M5 | 5 | Incident-driven scene adaptation and teammate command prototype completed | - Incident State parameters produce visible scene changes. - At least one hazard state changes based on Call Phase results. - Equipment recommendation is displayed before entering the scenario. - Bot teammate responds to at least two simple scripted commands. |
| M6 | 6 | MVP scenario alpha and reusable scenario framework completed | - The complete loop from Main Menu / Scenario Start → Call Phase → On-site → Result/Debrief runs without critical crashes. - The MVP scenario can be completed from start to finish. - Rank calculation and debrief prototype are displayed correctly. - The second scenario is integrated into the shared scenario-loading/configuration framework. - Internal alpha playtest is conducted and recorded. |
| M7 | 7 | Content-complete beta with two playable scenarios completed | - Both approved scenarios are playable end-to-end. - Scenario dialogue, mission content, and debrief text are content-complete. - Environment art pass and usability pass are applied. - Bot command flow and tool feedback are polished to beta level. - Internal beta playtest is completed and major issues are logged. |
| M8 | 8 | QA-tested and balanced two-scenario beta completed | - Formal test plan and test cases are completed. - Functional, integration, and UX testing are executed across both scenarios. - High-priority defects are fixed or downgraded. - Timer values, score thresholds, and mission pacing are balanced. |
| M9 | 9 | User evaluation completed and documents consolidated | - Small-scale user evaluation is conducted. - Evaluation results are summarized and analyzed. - Cross-scenario findings are reviewed and reflected in the final adjustments. - SRS, SDD/Architecture, Test Report, and Evaluation Report drafts are updated. - Near-final build is stable for final polishing. |
| M10 | 10 | Final two-scenario build, source, documents, slide, and demo delivered | - Final Windows build is generated successfully. - The build includes two playable scenarios. - Source code package is organized and ready for submission. - Final thesis report, test report, evaluation report, and user manual are completed. - Demo video and release/readme package are completed. |

## Task assignment / responsibility

Responsibilities are assigned according to the actual 3-member project team structure rather than a single-developer Scrum model.

Project Supervisor:

Provides academic guidance, reviews major milestones, and validates the project’s technical and educational direction.

Bùi Lê Đức Huy (Team Leader):

Responsible for overall technical integration, Unity programming, gameplay system implementation, architecture decisions, and 3D scene assembly. Huy is also the primary coordinator for sprint planning and milestone tracking.

Bùi Lê Đức Hiếu:

Responsible for Unity programming support, gameplay system implementation, UI/UX design, content integration, and writing support for design and technical documents.

Lê Tuấn Anh:

Responsible for writing/content support, QA planning and execution, playtest coordination, bug reporting, and evaluation/documentation support.

Team Collaboration Principle:

Although responsibilities are divided by specialization, implementation, testing, and documentation activities may overlap across members when required by sprint goals.

# Technical Approach Summary

## High-level architecture overview

The system is designed using a Modular State-Based Architecture. This ensures that the distinct phases of the game (Call, Simulation, Debrief) are decoupled, allowing for easier debugging and scalability.

Game Manager (FSM): A Finite State Machine (FSM) controls the global transitions between the Main Menu, Call Phase, On-site Simulation, and Result State.

Data Broker Layer: Acts as the bridge between the Call Phase and the On-site Phase. It takes the "Answers" from the player, runs them through a mapping logic, and generates a Mission Configuration Object.

Module Interaction Flow:

- Input: User answers in the Call Phase.

- Processing: The Incident State Engine calculates variables (Fire Intensity, Hazard Type, Victim Location).

- Instantiation: The Scenario Loader applies these variables to the Unity Scene (e.g., toggling specific fire prefabs or changing smoke density).

## Key technical decisions (ví dụ: data-driven scenarios, deterministic mapping)

### Data-Driven Scenario System

Instead of hard-coding every scenario, the project utilizes Unity Scriptable Objects.

Why: This allows for "Data-Driven" development. New fire situations can be created by simply creating a new Scriptable Object file without changing the underlying code.

Mechanism: Each question in the Call Phase is linked to a weight value. For example, failing to ask about "Gas" sets the gas_leak_active boolean to True, which triggers an explosion prefab in the On-site phase.

### Deterministic Parameter Mapping

To ensure educational consistency, the mapping from the Call Phase to the On-site Phase is Deterministic.

Logic: $Incident\_State = f(User\_Questions, Response\_Time)$.

This ensures that the same set of answers always results in the same hazard conditions, which is crucial for the "Cause-and-Effect" debriefing system.

### Mission Tree & Trigger System

The mission system uses a Prerequisite-based Trigger System. Missions are organized in a tree structure where "Task B" (e.g., Rescue Victim) cannot be completed until "Task A" (e.g., Breach Door) is finished. This enforces the Standard Operating Procedures (SOP).

## Dependencies (Unity packages, assets, tools)

Table 5.1 Dependencies Used in the Project

| Category | Tools / Packages | Purpose |
| --- | --- | --- |
| Engine | Unity 6.0 LTS (or newer) | Long-term support and stability. |
| Rendering | Universal Render Pipeline (URP) | Optimized for performance while maintaining high-quality VFX. |
| Input | Unity Input System Package | Support for Mouse/Keyboard and modularity. |
| AI | Unity NavMesh | Pathfinding for the squad bots and NPCs. |
| Assets | Synty/Unity Asset Store | Professional 3D models for firefighters, victims, and environments. |
| VFX | Visual Effect Graph / Particle System | Real-time fire, smoke, and water simulation. |

## Technical risks & mitigation (ngắn gọn)

Table 5.2 Project Technical Risks and Mitigation Measures

| Risk | Impact | Mitigation Strategy |
| --- | --- | --- |
| Performance Drops | High | Use Object Pooling for fire/smoke particles and optimize LODs (Level of Detail) for environment assets. |
| AI Navigation Errors | Medium | Use NavMesh Links to ensure bots can navigate through breached doors or over debris. |
| Logic Complexity | Medium | Implement strict Unit Testing for the Incident State mapping logic to ensure Call Phase data is correctly transferred. |
| Scope Creep | High | Adhere strictly to the MoSCoW prioritization; if AI commands become too complex, simplify to a basic "Follow/Stay" system. |

# Resource Management

## Team structure & roles

The project is developed by a 3-member student team with clearly defined functional responsibilities.

Bùi Lê Đức Huy – Team Leader, Unity Programmer, Game Designer, 3D Artist:

Responsible for core gameplay systems, technical integration, scene setup, architecture coordination, and milestone supervision.

Bùi Lê Đức Hiếu – Unity Programmer, Game Designer, UI/UX Designer, Writer/Content:

Responsible for gameplay implementation support, user interface design, interaction flow, content integration, and documentation support.

Lê Tuấn Anh – Writer/Content, QA:

Responsible for content writing support, QA planning and execution, playtest organization, bug reporting, and evaluation/report support.

The team structure is intentionally lightweight to match the capstone context, but responsibilities are distributed across technical, content, testing, and documentation workstreams.

## Tools & technology stack (Unity version, repo, CI nếu có)

The project utilizes a professional-grade development stack to ensure stability and compatibility.

Table 6.1 Development Tools and Software Used in the Project

| Category | Tool / Software | Purpose |
| --- | --- | --- |
| Game Engine | Unity 6.0 LTS | Primary development platform (Long-Term Support version). |
| Programming | Visual Studio 2022 / C# | IDE for scripting and logic implementation. |
| Version Control | Git / GitHub | Repository management and version history tracking. |
| Project Mgmt | Jira | Sprint planning, backlog tracking, task assignment, and progress monitoring across the 10-sprint project timeline. |
| 3D Modeling | Blender | Creating or modifying custom 3D assets and props. |
| Texturing/UI | Adobe Photoshop / Canva | Designing UI elements, icons, and textures. |
| Documentation | Microsoft Word / LaTeX | Preparing the final thesis report and technical docs. |

## Resource plan

### Hardware Requirements

Development and testing will be conducted on a mid-range Windows workstation/laptop representative of the project’s target deployment environment.

Reference Test Hardware:

- CPU: Intel Core i5-11th gen (or equivalent)

- RAM: 8 GB

- GPU: NVIDIA GeForce RTX 3050 Laptop GPU 6 GB VRAM or equivalent

- OS: Windows 11

- Display Target: 1920 × 1080

Testing Devices:

Standard Windows PC setup with mouse and keyboard for FPS gameplay.

### Asset Sourcing

To meet the 20-week deadline, a hybrid approach to asset creation is adopted:

- Sourced Assets: Low-poly or modular environment assets (e.g., Synty Studios or Unity Asset Store) will be used for buildings and characters to focus development time on core logic.

- Custom Assets: Specific firefighting tools (extinguishers, specific nozzles) and the UI/UX for the Call Phase will be custom-made to fit the project's unique educational requirements.

### Time Allocation

The project spans 20 weeks, with an estimated 15–20 hours per week dedicated to development, research, testing, and documentation. This schedule is managed through the 10-sprint plan defined in Chapter 4, with each sprint lasting 2 weeks.

# Risk Management

## Risk management approach

The project adopts a proactive risk management strategy consisting of four continuous phases:

- Identification: Regularly documenting potential threats during Sprint Planning.

- Assessment: Evaluating risks based on their Probability (Likelihood) and Impact (Severity on the final grade/functionality).

- Mitigation: Implementing actions to reduce the probability or impact of a risk.

- Monitoring: Reviewing the Risk Register during every Sprint Retrospective to update the status of each threat.

## Risk register

Table 7.1 Risk Register for the Project

| ID | Risk Description | Category | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| R1 | Scope Creep: Expanding scenario-specific content across two scenarios too early, leading to an unfinished or unstable core loop. | Project | High | Critical | Strictly prioritize shared core systems first, complete one MVP scenario before deepening secondary-scenario content, and apply MoSCoW-based scope control to scenario-specific features. |
| R2 | Technical Complexity: Difficulty in linking Call Phase variables to dynamic scene changes. | Technical | Medium | High | Develop a simplified "Proof of Concept" in Sprint 3 to validate the Data Broker logic early. |
| R3 | Performance Issues: High VFX (fire/smoke) causing frame rate drops on target hardware. | Technical | Medium | Medium | Use Object Pooling for particles and optimize URP settings. Test on target hardware early. |
| R4 | Time Management: Unexpected academic or personal delays during the 20-week period may prevent both scenarios from reaching the intended level of polish. | Project | High | Medium | Maintain a controlled end-phase buffer by limiting Sprint 9-10 to evaluation, stabilization, bug fixing, final polish, and document/package preparation. Enforce a feature freeze after Week 16 and, if needed, reduce the complexity of the secondary scenario before cutting core-loop functionality. |
| R5 | AI Pathfinding: Squad bots getting stuck or failing to follow complex commands. | Technical | Medium | Low | Simplify the command system to "Follow/Stay" if complex tasking takes too long to debug. |
| R6 | Asset Availability: Inability to find specific 3D models for firefighting tools or environments. | Resource | Low | Medium | Use modular asset packs from the Unity Store and prioritize functionality over visual realism. |

## Mitigation & contingency

To ensure a successful thesis defense even in the event of major delays, a Contingency Plan is established based on the MoSCoW priorities. If the project falls behind schedule by more than one Sprint, the following scope cuts will be implemented in order:

Level 1 Cut (Minor):

- Remove advanced visual effects such as volumetric lighting, heat haze, and non-essential environmental polish.

Level 2 Cut (Moderate):

- Simplify the Squad Command System to only essential commands such as Follow and Wait, removing more advanced contextual actions.

Level 3 Cut (Major):

- Reduce the content complexity of the secondary scenario by limiting non-essential interactions, advanced victim/randomization behaviors, extra tool variations, and secondary UI features that do not directly support the core learning loop.

Level 4 Cut (Emergency):

- Prioritize one fully polished MVP scenario for defense readiness while preserving the shared architecture and the implemented framework for scenario reuse as evidence of system scalability.

## Risk Ownership

Risk ownership is distributed across the 3-member project team according to work specialization.

- Huy is the primary owner of technical integration, performance, build stability, and scene adaptation risks.

- Hiếu is the primary owner of UI/UX consistency, content integration, and documentation consistency risks.

- Tuấn Anh is the primary owner of QA execution, evaluation logistics, and reporting quality risks.

Any risk with Critical impact must be reported to the Project Supervisor immediately for academic guidance and scope-control decisions.

# Progress Monitoring and Reporting

## Tracking metrics (burndown/checklist/bug count/playtest notes)

To ensure the project remains on schedule and meets the required quality standards, the following quantitative and qualitative metrics are tracked:

- Sprint Burndown Chart: A visual representation of work remaining versus time in each 2-week sprint. This helps in identifying if the development velocity is sufficient to meet the milestone deadlines.

- Feature Completion Checklist: A live document based on the MoSCoW priorities. Features are marked as "In Progress," "Testing," or "Done" based on the Definition of Done (DoD) defined in Chapter 3.

- Bug Count & Severity: Bugs discovered during internal testing are categorized as:

- Critical: Game-breaking or preventing the core loop.

- Major: Functional errors in non-critical systems.

- Minor: Visual glitches or UI polish issues.

- Playtest Feedback Notes: Qualitative data collected from peers or "target users" during the Beta phase. These notes focus on the Educational Efficacy (Is the debriefing clear?) and Usability (Are the controls intuitive?).

## Reporting cadence (weekly: done/next/blockers)

Effective communication with the Project Supervisor is maintained through a structured reporting schedule:

Table 8.1 Project Reporting Plan

| Report Type | Frequency | Content |
| --- | --- | --- |
| Weekly Status Sync | Every Week | A brief "Done/Next/Blockers" report. Focuses on immediate technical hurdles. |
| Sprint Review Report | Every 2 Weeks | A summary of the completed Sprint Goal, a demo of the functional increment, and an updated Risk Register. |
| Milestone Presentation | Monthly (M1-M4) | At major project gates (Prototype, Alpha, Beta, Final) A formal review of progress against the approved Project Plan, including scope status, build readiness, documentation status, and major risk updates. |
| Final Thesis Draft | Week 18–19 | Submission of the complete documentation for final review before the defense. |

## Artifact management (versioning docs, build naming, storage)

To maintain a professional workflow and prevent data loss, all project assets and documents are managed systematically.

### Version Control (Source Code)

Tool: Git hosted on GitHub.

Branching Strategy: * main: Stable, "Golden" versions of the game.

- develop: Integration branch for new features.

- feature/feature-name: Temporary branches for specific task development.

Link Git: https://github.com/bhuy1313/FF3D.git

### Build Naming & Versioning

Every executable build provided for testing or defense follows a semantic versioning convention: Major.Minor.Patch (e.g., v0.5.1_Alpha).

- Alpha Builds: Core mechanics functional but assets/VFX are unpolished.

- Beta Builds: Feature-complete; focus on balancing and bug fixing.

- Release Candidate (RC): Final builds ready for the thesis defense.

### Documentation & Asset Storage

Cloud Storage: Google Drive and OneDrive are used for non-code artifacts and controlled documents, including the Project Plan, Software Process and Quality Plan, BAD/ConOps, SRS, SDD, test artifacts, evaluation materials, 3D source files, textures, and meeting minutes.

Task Management: Jira is used as the primary project management tool to manage the Product Backlog, Sprint Backlog, issue tracking, and individual task assignments.

Approved document revisions follow a simple versioning and baseline-control practice so that major updates to scope, quality procedures, and deliverables can be traced across the documentation suite.

# Change Management

## Change request process

Despite following the Scrum framework, which welcomes iterative improvements, any significant deviation from the initial Project Plan or SRS must undergo a formal Change Request process. This prevents disorganized development and ensures that every change adds value to the educational goals.

The process follows four distinct steps:

- Proposal: The developer or supervisor identifies a necessary change (e.g., a new gameplay mechanic or a modification to the scoring rubric).

- Impact Analysis: The developer assesses how the change affects:

- Time: Will it delay the current Sprint or the final Milestone?

- Complexity: Does it require new assets or complex scripts that might introduce bugs?

- Prioritization: Does this change replace a "Must-Have" or "Should-Have" item?

- Decision: The developer consults with the Project Supervisor for approval. Decisions are based on whether the change is essential for the thesis's academic success.

- Implementation & Baseline Update: If approved, the Product Backlog is updated, and the change is documented in the Change Log.

## Scope control rules (chống scope creep)

To prevent Scope Creep (the uncontrolled expansion of project scope without adjustments to time or resources), the following rules are strictly enforced:

- The "One-In, One-Out" Rule: If a new "Should-Have" feature is added to the In-Scope list, a feature of equal development effort must be moved to the "Could-Have" or "Out-of-Scope" list to maintain the 20-week timeline.

- MoSCoW Adherence: No "Could-Have" features will be developed until all "Must-Have" features are fully functional and pass the Definition of Done (DoD).

- Feature Freeze (Week 16): After Week 16, no new features or major logic changes can be introduced. The remaining 4 weeks are strictly reserved for bug fixing, UI polish, and documentation finalization.

- Code Stability Priority: Any change that threatens the stability of the Core Loop (Call Phase $\rightarrow$ On-site $\rightarrow$ Debrief) will be rejected regardless of its potential visual or gameplay appeal.

# Test & Validation Plan Summary

## Test strategy overview (unit/integration/playmode)

To ensure the reliability and educational accuracy of Ignis Guard, a multi-layered testing strategy is employed. Testing occurs continuously throughout the sprints, moving from individual components to full gameplay-loop validation and user evaluation.

- Unit Testing: Individual C# scripts and logic modules (e.g., the scoring algorithm, timer logic, and the Data Broker’s mapping functions) are tested in isolation to ensure mathematical and logical correctness.

- Integration Testing: Focuses on the communication between modules. Specifically, verifying that the Incident State generated in the Call Phase correctly triggers the intended environmental changes (VFX spawning, hazard activation) in the On-site Phase.

- Playmode/Manual Testing: Regular walk-throughs of the game within the Unity Editor and in standalone builds to identify issues with physics collisions, UI responsiveness, and AI pathfinding.

- User Acceptance Testing (UAT): Conducted during the Beta and near-final phases using an accessible evaluation sample such as students and peers available to the team. The purpose is to evaluate usability (controls, UI clarity, interaction flow) and educational efficacy (whether the debriefing successfully communicates the cause-and-effect of player decisions).

## Validation against SRS (FR/NFR coverage)

Validation ensures that the final product aligns with the Software Requirement Specification (SRS). A Requirements Traceability Matrix is used to map test cases to specific requirements.

### Functional Requirements (FR) Validation

Scenario Coverage: Validation that both approved scenarios load the correct map, mission configuration, hazard setup, and asset context.

Core Loop Integrity: Success is defined as the ability to move from Main Menu / Scenario Start → Call Phase → On-site → Result/Debrief without any critical crashes on each implemented scenario.

Mission Logic: Ensuring that mission objectives are only marked as complete when the specified interaction conditions are met within the selected scenario.

Cross-Scenario Consistency: Validation that shared systems such as Call Phase, Incident State mapping, scenario loading, scoring, and debriefing behave consistently while still applying scenario-specific content correctly.

### Non-Functional Requirements (NFR) Validation

Performance: The game is validated using the Unity Profiler to target an average of 60 FPS during normal gameplay and to maintain a minimum acceptable threshold of 30 FPS on the reference hardware specified in Chapter 6 across both scenarios.

Accuracy: Validation of Incident State mapping, fire-response logic, and SOP-based scoring against the intended training logic approved by the supervisor.

Usability: Ensuring that the UI is legible, controls are understandable, scenario selection is clear, and the teammate command interface is accessible through simple hotkeys or minimal interaction steps.

## Demo checklist

The following checklist represents the "Minimum Functional Criteria" that must be operational during the final thesis defense:

Table 10.1 Demo Checklist by Milestone

| Category | Requirement | Verification Method |
| --- | --- | --- |
| System | Build launches successfully and allows the user to select between two playable scenarios. | Live Execution |
| Call Phase | Timer works; user can select answers; Incident State is saved correctly. | Live Gameplay |
| On-site | Scene parameters (fire/smoke/hazards) reflect Call Phase choices in the selected scenario. | Visual Inspection |
| Mechanics | Firefighting interaction works; the player can complete at least one core objective in each scenario. | Live Gameplay |
| Squad AI | Bot follows at least one basic command (e.g., "Follow Me"). | Live Gameplay |
| Evaluation | Result screen displays a rank (C-S) and a logic-based debriefing text for the completed scenario. | Live Gameplay |

# Lessons Learned & Recommendations

## Lessons learned

Based on the planned 20-week development lifecycle and the technical constraints identified during project planning, several key lessons and guiding considerations have been identified across technical, pedagogical, and project management domains.

- Technical Integration (The Data Bridge): One of the primary lessons was the complexity of mapping subjective Q&A data from the Call Phase to objective environmental parameters in Unity. The transition from a 2D UI-based minigame to a 3D physical environment required a robust "Data Broker" layer to prevent logic conflicts.

- Performance vs. Realism: Balancing high-fidelity VFX (fire and smoke) with the need for stable performance (60 FPS) was a significant challenge. Early optimization using Object Pooling and URP Shader Graph proved more effective than attempting to use high-poly assets.

- Scrum in a Small-Team Capstone Context: While Scrum is often discussed in larger team settings, its iterative nature remains effective for a 3-member capstone team. A 2-week Definition of Done for each feature helps control scope, expose blockers early, and keep the core loop functional well before the final deadline.

- Serious Game Design: Designing for education is different from designing for entertainment. It was learned that "punishing" a player for a mistake is less effective than providing a clear "Cause-and-Effect" debriefing that explains why a specific action led to a failure.

## Recommendations / future work

While the current project fulfills the requirements of the capstone thesis, several avenues for expansion exist to increase its utility as a professional training tool.

### Technical Enhancements

VR/AR Integration: Porting the simulation to Virtual Reality (VR) platforms like Meta Quest 3 to enhance spatial awareness and provide a more immersive "On-site" experience for trainees.

Advanced Fire Dynamics: Implementing a more sophisticated cellular automata or fluid-based fire spread system to replace the current particle-based approach for greater realism.

Multiplayer Cooperation: Expanding the Squad Command System into a networked multiplayer mode, allowing a Team Leader and multiple firefighters to coordinate in real-time.

### Content Expansion

Diverse Scenario Library: Expanding beyond the initial two approved scenarios into specialized modules for industrial chemical fires, forest fires, or high-rise evacuation variations, each with unique SOPs and hazards.

Dynamic AI Dialogue: Utilizing Large Language Models (LLMs) or AI-driven voice synthesis in the Call Phase to create more natural and unpredictable interactions with callers.

### Educational Integration

LMS Compatibility: Integrating the simulation’s scoring system with Learning Management Systems (LMS) like Moodle or Canvas to allow instructors to track student progress over time.

Haptic Feedback: Utilizing haptic vests or gloves to simulate the physical strain and heat of a firefighting environment, further bridging the gap between virtual and real-world training.

# CONCLUSION

This Project Plan defines a structured and feasible roadmap for the design and development of Ignis Guard, a simulation-based game application for fire prevention and firefighting training. The project is scoped as a two-scenario serious game developed over 10 sprints across 20 weeks, with a clear focus on delivering a shared training architecture that integrates the core gameplay loop: Call Phase, Incident State generation, On-site firefighting operations, and Result/Debrief evaluation.

The plan establishes the project’s scope, development process, sprint schedule, team responsibilities, quality strategy, risk management approach, and delivery expectations. By structuring the project around one polished MVP scenario and one additional implemented scenario built on the same core systems, the team can maintain a realistic workload while still demonstrating both the project’s educational value and the scalability of its architecture. In particular, the plan emphasizes deterministic scenario adaptation based on Call Phase information, SOP-aligned mission flow, and cause-and-effect debriefing to support player learning and replayability.

In addition, the plan provides a practical framework for project control through backlog management, milestone-based reviews, testing activities, documentation updates, and contingency planning. These mechanisms are intended to reduce schedule risk, improve development visibility, and ensure that the final product remains aligned with both academic requirements and the project’s intended educational objectives.

Overall, this Project Plan serves as the baseline for executing, monitoring, and evaluating the development of Ignis Guard. It provides a clear foundation for the team to progress from planning and design into implementation, testing, evaluation, and final delivery in a controlled and academically grounded manner.

# REFERENCES

Tiếng Anh:

[1] International Organization for Standardization, International Electrotechnical Commission, & Institute of Electrical and Electronics Engineers. (2017). ISO/IEC/IEEE 12207:2017 Systems and software engineering — Software life cycle processes.

[2] Institute of Electrical and Electronics Engineers. (2018). ISO/IEC/IEEE 29148-2018 Systems and software engineering — Life cycle processes — Requirements engineering.

[3] International Organization for Standardization. (2011). ISO/IEC 25010:2011 Systems and software engineering — Systems and software Quality Requirements and Evaluation (SQuaRE) — System and software quality models.

[4] Institute of Electrical and Electronics Engineers. (2016). IEEE Std 1012-2016: Standard for System, Software, and Hardware Verification and Validation.

[5] Schwaber, K., & Sutherland, J. (2020). The Scrum Guide.

[6] Sommerville, I. (2016). Software Engineering (10th ed.). Pearson.

[7] Pressman, R. S., & Maxim, B. R. (2020). Software Engineering: A Practitioner’s Approach. McGraw-Hill.

[8] Bass, L., Clements, P., & Kazman, R. (2012). Software Architecture in Practice (3rd ed.). Addison-Wesley.

[9] Project Management Institute. (2021). A Guide to the Project Management Body of Knowledge (PMBOK® Guide) (7th ed.). PMI.

[10] Michael, D., & Chen, S. (2005). Serious Games: Games That Educate, Train, and Inform. Course Technology.

[11] Salen, K., & Zimmerman, E. (2004). Rules of Play: Game Design Fundamentals. MIT Press.

[12] Schell, J. (2019). The Art of Game Design: A Book of Lenses (3rd ed.). CRC Press.

[13] Fullerton, T. (2018). Game Design Workshop: A Playcentric Approach to Creating Innovative Games (4th ed.). CRC Press.

[14] Unity Technologies. (n.d.). Unity Manual.

[15] Unity Technologies. (n.d.). Unity Scripting API.

Tiếng Việt:

[1] Trường Đại học Văn Lang, Khoa Kỹ thuật Cơ điện và Máy tính. (2025). Hướng dẫn thực hiện Đồ án Tốt nghiệp Kỹ thuật Phần mềm (Software Engineering Capstone Project Guidebook). TP. Hồ Chí Minh.

[2] Quốc hội nước Cộng hòa xã hội chủ nghĩa Việt Nam. (2024). Luật Phòng cháy, chữa cháy và cứu nạn, cứu hộ, số 55/2024/QH15. (Bộ Công an)

[3] Chính phủ. (2025). Nghị định số 105/2025/NĐ-CP quy định chi tiết một số điều và biện pháp thi hành Luật Phòng cháy, chữa cháy và cứu nạn, cứu hộ. (VBPL)

[4] Bộ Công an. (2024). Những điểm mới của Luật Phòng cháy, chữa cháy và cứu nạn, cứu hộ. (Bộ Công an)

[5] Bộ Xây dựng. (2022). QCVN 06:2022/BXD – Quy chuẩn kỹ thuật quốc gia về an toàn cháy cho nhà và công trình. (VBPL)

[6] Bộ Xây dựng. (2023). Sửa đổi 1:2023 QCVN 06:2022/BXD – Quy chuẩn kỹ thuật quốc gia về an toàn cháy cho nhà và công trình. (VBPL)