## Project Sprint Plan
Sprint | Goal | Detailed Tasks | Assigned Members | Deliverables
Sprint 1 | Project initiation and two-scenario scope definition | Define project vision, learning objectives, and project baseline; confirm the two approved scenarios and identify one as the MVP validation scenario; define the shared gameplay loop (Call Phase → Incident State → Preparation → On-site → Result/Debrief); set up Unity project, repository, Git workflow, folder structure, and naming conventions; draft initial backlog; prepare initial outlines for GDD, SRS, and risk list. | Huy: Unity project setup, repo, technical baseline. | Project scope baseline; approved two-scenario concept; designated MVP scenario; product backlog v1; Unity project/repository setup; GDD outline; SRS outline; initial risk register.
Hieu: gameplay loop draft, UI flow draft, initial GDD/SRS structure.
Tuấn Anh: scenario concept, learning goals, initial risk list.
Sprint 2 | Pre-production design and architecture for two scenarios | Finalize detailed design for both scenarios; define caller background, hazards, victim hints, and win/fail conditions for each scenario; design the rule-based branching dialogue tree; define shared Incident State parameters and scenario-specific rule mappings; design mission tree and scoring rubric; prepare architecture design, architecture drivers, and UI wireframes. | Huy: system architecture, data model design, technical feasibility. | Two-scenario design specification; dialogue tree specification; Incident State model specification; mission/scoring specification; software architecture draft; UI wireframes.
Hieu: UI wireframes, dialogue structure, SRS/GDD development.
Tuấn Anh: scenario writing, SOP mapping, scoring/debrief content draft.
Sprint 3 | Core framework and Call Phase prototype | Implement scene/game flow controller; create data structures for scenario, dialogue, Incident State, missions, and scoring; build Call Phase prototype with timer/turn limit and question-answer tracking; implement rule-based branching logic; create prototype Incident State calculator and equipment recommendation logic; create Call Phase UI prototype; run initial functional tests. | Huy: core architecture code, state flow, data systems. | Playable Call Phase prototype; Incident State calculation prototype; equipment recommendation prototype; updated technical notes.
Hieu: Call Phase UI, dialogue implementation, content hookup.
Tuấn Anh: dialogue content refinement, test checklist for Call Phase.
Sprint 4 | On-site gameplay foundation | Implement FPS movement and look controls; build interaction system (doors, switches, hotspots, simple object use); create blockout scenes for the approved scenarios; place hazards, triggers, and possible victim locations; create prototype tools (e.g., extinguisher, flashlight); build basic fire/smoke placeholders; create mission tracker prototype and HUD. | Huy: FPS controller, interaction system, scene blockout, triggers. | On-site prototype framework; scenario blockout scenes; FPS movement and interaction system; tool use prototype; objective tracker prototype.
Hieu: HUD/UI, tool interaction support, objective display.
Tuấn Anh: objective content logic, on-site test case drafting.
Sprint 5 | Incident-driven scene adaptation and teammate command system | Implement mapping from Incident State parameters to scene changes; enable/disable hazards based on call information; adjust smoke/fire levels and victim hint placement; create equipment recommendation briefing screen; implement simple scripted teammate commands (follow, wait, inspect, assist); connect bot actions to selected tasks; test the Call-to-On-site data pipeline across both scenario configurations. | Huy: scene adaptation system, bot logic, trigger integration. | Working scene adaptation system; equipment recommendation screen; teammate command prototype; end-to-end data pipeline prototype; scenario rule tables for both scenarios.
Hieu: command UI, preparation/briefing UI, data hookup.
Tuấn Anh: validation of rule tables, QA matrix for scenario variants.
Sprint 6 | Full gameplay loop integration for MVP scenario and reusable scenario framework | Integrate main menu, Call Phase, preparation, On-site Phase, and Result/Debrief into one complete loop; implement mission tree logic and success/failure rules; implement scoring calculation and rank mapping (C–S); create debrief logic with cause-effect educational feedback; complete first full integration on the MVP scenario; integrate the second scenario into the shared loading/configuration framework; conduct first internal playtest; update design/architecture documents to match implementation. | Huy: mission/scoring backend, overall integration. | End-to-end MVP scenario alpha; reusable scenario-loading/configuration framework; scoring/ranking system; debrief prototype; internal playtest report; updated GDD/SRS/architecture docs.
Hieu: result/debrief UI, scene flow polish, content linkage.
Tuấn Anh: debrief content, playtest notes, bug logging.
Sprint 7 | Content completion for both approved scenarios | Finalize scenario content, dialogue, mission triggers, victim logic, and hazard presentation for both approved scenarios; improve tool usage feedback; improve teammate command usability; polish environments using asset store/prototype assets; improve audio placeholders; conduct second internal playtest focused on clarity, pacing, learning value, and cross-scenario consistency. | Huy: scene polish, gameplay feel, technical fixes. | Content-complete beta build with two playable scenarios; refined scenario scripts; improved mission/debrief content; playtest round 2 report.
Hieu: UI polish, content integration, feedback improvements.
Tuấn Anh: final writing, rubric refinement, regression QA.
Sprint 8 | QA, balancing, and evaluation preparation | Create formal Test Plan and detailed test cases; perform functional, integration, and UX testing; test Call branches, Incident mapping, mission progression, score/rank correctness, and bot commands across both scenarios; fix high-priority and medium-priority bugs; balance timer limits, mission pacing, and score thresholds; prepare educational/usability evaluation method and questionnaires. | Huy: gameplay/system bug fixing, balancing. | Test Plan; test cases; bug list and fix log; evaluation plan; balanced beta build validated across both scenarios.
Hieu: UI/UX fixes, score/debrief refinement, test support.
Tuấn Anh: test documentation, QA execution, evaluation instruments.
Sprint 9 | User evaluation and documentation consolidation | Conduct small-scale user evaluation; collect feedback on usability, perceived learning value, gameplay clarity, and debrief usefulness across the implemented scenarios; analyze evaluation results; implement major fixes from user feedback; finalize GDD, SRS, architecture document, Test Report, Evaluation Report draft; prepare thesis/report draft, slide outline, and demo script. | Huy: technical stabilization, architecture input finalization. | Evaluation summary; near-final two-scenario build; finalized technical documents; thesis/report draft; demo script.
Hieu: report drafting, slide structure, UI polish.
Tuấn Anh: evaluation execution, data analysis summary, QA regression, report support.
Sprint 10 | Final polish, packaging, and delivery | Perform final bug fixing and optimization pass; finalize UI/UX polish and balancing; create Windows release build; clean and organize source code; prepare README, install guide, and asset attribution; finalize thesis/report, demo video, screenshots, and appendix materials; rehearse final demo and defense presentation. | Huy: final build, source cleanup, performance fixes. | Final Windows build with two playable scenarios; source code package; final thesis/report; demo video; final Test Report; final Evaluation Report; release/readme package.
Hieu: final UI polish, slide/demo support, packaging documentation.
Tuấn Anh: final QA pass, proofreading, rehearsal notes.