BỘ GIÁO DỤC VÀ ĐÀO TẠO TRƯỜNG ĐẠI HỌC VĂN LANG KHOA KỸ THUẬT CƠ ĐIỆN VÀ MÁY TÍNH CAPSTONE PROJECT – GROUP 15 Design and Development of a Simulation-Based Game Application for Fire Prevention and Firefighting Training Major: Software Engineering Document: SOFTWARE PROCESS AND QUALITY PLAN Version: 1.3 ¦ Date created: January 3rd, 2026 Group Student: BÙI LÊ ĐỨC HUY*; 2274801030183. BÙI LÊ ĐỨC HIẾU; 2274801030046. LÊ TUẤN ANH; 2274801030228. Mentor: Ths. Lã Hoàng Quý Hồ Chí Minh City – January 3rd, 2026

# REVISION HISTORY

| Project Information Overview |  |  |
| --- | --- | --- |
| Project Title | Design and Development of a Simulation-Based Game Application for Fire Prevention and Firefighting Training |  |
| Product Name | Ignis Guard |  |
| Project Mentor | Ths. Lã Hoàng Quý |  |
| Partner Organization | No external partner organization |  |
| Team members | Bùi Lê Đức Huy* | 2274801030183 |
|  | Bùi Lê Đức Hiếu | 2274801030046 |
|  | Lê Tuấn Anh | 2274801030228 |

| Document Information |  |  |
| --- | --- | --- |
| Document Title | SOFTWARE PROCESS AND QUALITY PLAN |  |
| Author(s), Role(s) | Bùi Lê Đức Huy | Team Leader, Unity Programmer, Game Designer, 3D Artist |
|  | Bùi Lê Đức Hiếu | Unity Programmer, Game Designer, UI/UX Designer, Writer/Content |
|  | Lê Tuấn Anh | Writer/Content, QA, Game Designer |
| Changelog | 3/1/2026 – v1.0 | Initial version of the Software Process and Quality Plan created as a companion document to the Project Plan for Group 15. |
|  | 17/2/2026 – v1.1 | Refined the process model, lifecycle phases, Scrum ceremonies, roles, and project artifacts for consistency with the approved Project Plan. |
|  | 8/3/2026 – v1.2 | Finalized quality objectives, QA/QC/QI activities, verification and validation, change control, and monitoring metrics. |
|  | 29/4/2026 – v1.3 | Updated scope description from single-player to squad-based tactical simulation (Ch. 1); expanded Table 2.1 with change control, risk management, and quality gate trigger rows; added Squad AI Correctness and Seed Determinism quality objectives to Table 7.1; updated Beta gate in Table 7.3 to reflect implemented systems (cluster-based fire, ToolWheel, Squad AI); added IncidentSeedUtility determinism test scenario to Table 8.1; added Supervisor Notification step to change control process (Table 9.1); updated Risk-Control Rules to protect Must-Have Squad AI from scope reduction (Ch. 9.3); clarified milestone review frequency in Table 10.1. |

# TABLE OF CONTENTS

REVISION HISTORY	2

TABLE OF CONTENTS	5

LIST OF TABLES	6

Chapter 1.	Introduction and Scope	7

Chapter 2.	Selected Software Process Model	8

Chapter 3.	Lifecycle Phases, Activities, Inputs, and Outputs	10

Chapter 4.	Sprint Governance and Working Rules	13

Chapter 5.	Roles and Responsibilities	15

Chapter 6.	Work Products and Deliverables	17

Chapter 7.	Quality Management Approach	19

7.1	Quality Objectives	19

7.2	QA, QC, and Improvement Activities	21

7.3	Definition of Done and Quality Gates	22

Chapter 8.	Verification and Validation Approach	23

8.1	Validation Focus Areas	24

Chapter 9.	Configuration, Change, and Risk Control	25

9.1	Configuration Management	25

9.2	Change Control	25

9.3	Risk-Control Rules	26

Chapter 10.	Metrics, Reporting, and Corrective Action	27

10.1	Corrective Action Policy	28

Conclusion	29

# LIST OF TABLES

Table 2.1 Process Model Selection and Supporting Evidence	8

Table 3.1 Overview of the Ignis Guard Development Lifecycle	10

Table 4.1 Agile Scrum Control Activities for Ignis Guard	13

Table 5.1 Role Assignment and Process Participation	15

Table 6.1 Project Documentation Artifacts and Ownership	17

Table 7.1 Quality Objectives for the Ignis Guard Project	19

Table 7.2 QA, QC, and Quality Improvement Activities and Outputs	21

Table 7.3 Quality Gates and Expected Readiness Conditions	22

Table 8.1 Verification Levels and Supporting Test Evidence	23

Table 9.1 Steps in the Project Change Management Process	25

Table 10.1 Progress Monitoring Reports and Corrective Triggers	27

# Introduction and Scope

The scope of this plan covers the full software development lifecycle of Ignis Guard as a capstone-scale serious game developed for PC Windows. The project is implemented as a squad-based tactical simulation built on a shared gameplay architecture and delivered through two playable scenarios.

The planned product includes a complete educational gameplay loop consisting of the Call Phase, Incident State mapping, On-site gameplay, and Result/Debrief evaluation. One scenario serves as the MVP validation baseline for milestone review and focused polishing, while the second scenario is implemented on the same core systems to demonstrate architectural reuse, content scalability, and cross-scenario consistency.

This plan therefore governs not only the development of the core systems, but also the quality controls, review practices, and validation activities required to ensure that both approved scenarios remain aligned with the project’s educational and technical objectives.

# Selected Software Process Model

Ignis Guard follows an Agile Scrum process enhanced with milestone-based quality gates. This selection is appropriate because the project includes iterative gameplay tuning, content balancing, educational feedback refinement, and repeated playtesting. These characteristics benefit from short feedback loops rather than a rigid one-pass sequence.

The Scrum process is supported by a 2-week sprint cadence, backlog-driven planning, continuous integration into a shared codebase, and structured end-of-sprint reviews. At a higher level, the team still works through recognizable SDLC phases: planning, analysis, design, implementation, testing, evaluation, and finalization.

Table 2.1 Process Model Selection and Supporting Evidence

| Process Characteristic | Chosen Approach | Why It Fits Ignis Guard | Evidence Source |
| --- | --- | --- | --- |
| Sprint structure | 10 sprints × 2 weeks | Creates a manageable 20-week delivery rhythm for one polished MVP scenario and one additional implemented scenario built on the same shared architecture. | Project Plan Chapters 2–4 |
| Core process model | Agile Scrum | Supports iterative gameplay development and frequent refinement of content, UI, and learning feedback. | Project Plan Chapter 4 |
| Change control approach | Formal 5-step change request process (Proposal → Impact Analysis → Decision → Implementation → Supervisor Notification) | Small team operating under fixed capstone timeline requires structured control to prevent baseline drift. | SPQP Chapter 9.2 |
| Risk management approach | MoSCoW prioritization + sprint-level risk review + Week 16 stabilization freeze | Protects MVP delivery under capstone timeline constraints and scope uncertainty. | Project Plan risk register; SPQP Chapter 9.3 |
| Quality gate trigger | At each of four milestone gates: Prototype, Alpha, Beta, Final | Gates enforce milestone readiness and provide supervisor review checkpoints distributed across the 20-week delivery schedule. | SPQP Chapter 7.3; Project Plan milestones |

Process Principles

- Deliver one polished MVP scenario first, then extend the validated architecture to the second approved scenario before investing in advanced effects or non-essential polish.

- Use MoSCoW prioritization to protect feasibility and prevent scope creep.

- Make quality visible at every sprint through Definition of Done, bug tracking, and playtest evidence.

- Treat documentation, testing, and evaluation as active work products, not end-of-project afterthoughts.

# Lifecycle Phases, Activities, Inputs, and Outputs

The project uses Scrum for day-to-day execution, but the overall work is still organized into lifecycle phases. Each phase has defined activities, expected inputs, outputs, review events, and responsible owners.

Table 3.1 Overview of the Ignis Guard Development Lifecycle

| Phase | Approx. Sprints | Main Activities | Key Inputs | Outputs / Deliverables | Review / Exit Criteria |
| --- | --- | --- | --- | --- | --- |
| 1. Initiation and Planning | Sprint 1 | Define project vision, learning objectives, two-scenario scope, MVP baseline scenario, initial backlog, repository setup, and risk baseline. | Guidebook expectations, mentor direction, project idea | Project Plan baseline, backlog v1, initial risk register, repo and folder structure | Scope baseline approved; two scenarios identified; one scenario designated as MVP baseline |
| 2. Analysis and Scenario Design | Sprint 2 | Finalize the two approved scenarios, dialogue tree structure, Incident State parameters, mission logic, scoring concept, and SOP mapping for the shared architecture. | Project vision, target users, scenario concepts | BAD/ConOps refinement, SRS inputs, two-scenario specification, scoring/debrief draft | Requirements and design assumptions reviewed with mentor |
| 3. Architecture and Technical Design | Sprint 2–3 | Design state flow, data model, UI wireframes, architecture decisions, and content structures. | Approved scope and requirements | SDD / architecture draft, UI wireframes, data contracts, design notes | Design baseline supports implementation |
| 4. Iterative Implementation | Sprint 3–6 | Implement Call Phase, Incident State mapping, On-site mechanics, bot commands, scoring, debriefing, and reusable scenario-loading/configuration logic. | Backlog, technical design, content assets | Playable increments, source code, prototype builds, updated docs, shared scenario framework | Features meet Definition of Done and support the shared two-scenario architecture |
| 5. Integration, QA, and Balancing | Sprint 7–8 | Integrate the complete gameplay loop, run tests, fix defects, balance timers and scoring, validate both scenarios, and prepare evaluation instruments. | Integrated build, test plan, test cases | Balanced beta build, bug log, QA evidence, evaluation plan, cross-scenario validation results | High-priority defects reduced; beta quality gate passed across both implemented scenarios |
| 6. Evaluation and Finalization | Sprint 9–10 | Conduct user evaluation, apply final fixes, finalize documents, package source/build, and prepare defense materials for the final two-scenario build. | Near-final build, updated docs, evaluation tools | Evaluation Report, final build, source package, thesis artifacts | Final package complete, stable, and includes both approved scenarios |

# Sprint Governance and Working Rules

The project is executed through ten 2-week sprints. Sprint work is managed in Jira, source code is managed through Git/GitHub, and non-code artifacts are stored in shared cloud storage. Each sprint produces a demonstrable increment and an updated view of progress, quality, and risk.

Table 4.1 Agile Scrum Control Activities for Ignis Guard

| Ceremony / Control | Frequency | Primary Purpose | Main Owner |
| --- | --- | --- | --- |
| Sprint Planning | Start of each sprint | Define sprint goal, select backlog items, confirm ownership and acceptance expectations. | Team Leader with whole team |
| Daily Sync / Stand-up | Daily or near-daily | Share progress, blockers, and short-term adjustments. | Whole team |
| Sprint Review | End of each sprint | Demonstrate working increment and assess sprint goal completion. | Whole team + supervisor when applicable |
| Retrospective | End of each sprint | Identify process improvements, communication issues, and corrective actions. | Whole team |
| Milestone Review | At quality gates | Assess readiness for Prototype, Alpha, Beta, and Final stages. | Supervisor + team |

Working Rules

- The sprint backlog is frozen after sprint planning except for critical bug work or mentor-approved changes.

- All major scope changes must follow the formal change request process before being added to the active baseline.

- A feature cannot be marked Done unless it is implemented, integrated, stable, and documented.

- New major features should not be added after Week 16; the final phase is reserved for stabilization, evaluation, packaging, and documentation.

# Roles and Responsibilities

Process ownership is shared across the 3-member team, but each member has a clear primary responsibility area. The supervisor acts as the main academic reviewer and quality checkpoint authority rather than a day-to-day operator.

Table 5.1 Role Assignment and Process Participation

| Role | Name | Primary Responsibilities | Process Involvement |
| --- | --- | --- | --- |
| Project Supervisor | Ths. Lã Hoàng Quý | Provide academic guidance, review milestones, and validate technical and educational alignment. | Approval, review, feedback, milestone oversight |
| Team Leader / Unity Programmer / Game Designer / 3D Artist | Bùi Lê Đức Huy | Technical integration, gameplay systems, architecture decisions, scene assembly, milestone coordination. | Sprint planning, integration control, risk follow-up, technical sign-off |
| Unity Programmer / UI-UX Designer / Writer-Content | Bùi Lê Đức Hiếu | UI/UX design, implementation support, interaction flow, content integration, technical document support. | Implementation, UI review, documentation support, build packaging |
| Writer-Content / QA / Game Designer | Lê Tuấn Anh | QA planning and execution, playtest coordination, bug reporting, evaluation support, content support. | Test preparation, QA evidence, regression checks, evaluation analysis |

Responsibility Principle

Although each member has a specialization, quality is treated as a shared responsibility. A sprint increment is only considered acceptable when implementation, testing, and documentation expectations have all been met.

# Work Products and Deliverables

The process produces both management artifacts and engineering artifacts. Each artifact must support traceability from problem understanding through final validation.

Table 6.1 Project Documentation Artifacts and Ownership

| Artifact | Purpose | Primary Owner | Lifecycle Timing |
| --- | --- | --- | --- |
| Project Plan | Define scope, schedule, resources, risks, and project controls. | Team leader + whole team | Initiation and ongoing updates |
| Software Process and Quality Plan | Define process model, quality controls, and governance rules. | Whole team | Initiation; updated when process changes |
| BAD / ConOps | Describe context, stakeholders, operational scenarios, and usage assumptions. | Content + analysis contributors | Analysis and refinement |
| SRS | Define functional and non-functional requirements. | Whole team | Analysis and controlled updates |
| SDD / Architecture Design | Define architecture, components, data flow, and technical rationale. | Technical leads | Design and iterative refinement |
| Test Plan and Test Cases | Define test coverage, methods, expected results, and responsibilities. | QA owner with team support | QA preparation phase |
| Test Report | Capture test execution results, defect findings, and retest evidence. | QA owner | QA and finalization |
| Evaluation Report | Summarize user evaluation findings and their impact on the final build. | QA owner + whole team | Evaluation phase |
| Build Package and Source Code Package | Provide executable product and reproducible project assets. | Technical team | Finalization |

# Quality Management Approach

Quality management in Ignis Guard combines software quality assurance (QA), quality control (QC), and continuous improvement. The goal is not only to avoid defects, but also to ensure that the shared gameplay architecture is technically stable, educationally coherent, and sufficiently robust across the two approved scenarios.

Because the project is implemented as a capstone-scale serious game, quality management must remain practical and evidence-driven. The team therefore focuses on a disciplined set of controls covering implementation quality, scenario consistency, testing readiness, documentation synchronization, and educational validation through milestone-based review.

## Quality Objectives

Table 7.1 Quality Objectives for the Ignis Guard Project

| Quality Objective | Target | Measurement Method | Source of Acceptance |
| --- | --- | --- | --- |
| Performance | Average 60 FPS during normal gameplay; minimum 30 FPS under test conditions. | Profiling and supervised playtests on target hardware. | Project success metrics |
| Reliability / Stability | No critical game-breaking defects in the shared core gameplay loop and no unresolved blocking defects that prevent either approved scenario from being completed end to end. | Defect severity log and regression retesting. | Definition of Done and final acceptance |
| Deterministic Mapping Accuracy | The same Call Phase input set must produce the same Incident State and the correct scenario-specific result under the selected scenario configuration. | Logic tests, repeated scenario runs, and integration checks. | Technical objective and validation evidence |
| Educational Effectiveness | Users should identify at least 80% of their major tactical mistakes through debriefing. | Playtest observation and evaluation questionnaire analysis (minimum 5 users to produce a valid sample). | Project success metrics |
| SOP Alignment | Mission structure and safety priorities must align with supervisor-approved firefighting SOP logic across both implemented scenarios. | Content review, mentor review, scenario walkthrough. | Educational objective and milestone review |
| Maintainability / Documentation | Core systems and scenario-specific configurations are documented, and all major artifacts remain synchronized with the implemented build. | Documentation review during sprint and milestone checks. | Definition of Done and final package review |
| Squad AI Correctness | Squad bots must correctly execute all assigned commands (Extinguish, Rescue, Breach) with no unresponsive or misrouted command instances during integration testing. | Integration test cases covering each bot command type; pass/fail records per command. | Technical objective and integration test evidence |
| Seed Determinism | The same seed value must produce an identical world state across repeated runs (minimum 3 runs per seed tested). | Run IncidentSeedUtility with the same seed 3 times; compare resulting world state snapshots for full equivalence. | Technical objective and determinism test records |

## QA, QC, and Improvement Activities

Table 7.2 QA, QC, and Quality Improvement Activities and Outputs

| Control Layer | Purpose | Typical Activities | Outputs |
| --- | --- | --- | --- |
| Quality Assurance (QA) | Prevent defects and improve discipline before testing. | Document review, acceptance criteria definition, checklist preparation, peer walkthroughs, mentor feedback incorporation. | Reviewed artifacts, clarified criteria, improved process compliance |
| Quality Control (QC) | Detect defects and non-conformities in the product. | Functional tests, integration tests, playtests, defect logging, retests, balance checks. | Bug list, test results, defect status, build quality evidence |
| Quality Improvement (QI) | Refine both product and process based on evidence. | Retrospectives, corrective action notes, tuning changes, workflow adjustments, content revisions. | Process refinements, improved usability, reduced defect recurrence |

## Definition of Done and Quality Gates

A feature is Done only when it is functional, integrated into the main development line, stable during playtests, performance-safe for the target platform, and adequately documented. At the project level, the team also uses milestone quality gates for Prototype, Alpha, Beta, and Final readiness.

Table 7.3 Quality Gates and Expected Readiness Conditions

| Gate | Expected Readiness Condition |
| --- | --- |
| Prototype | Core movement and Call Phase UI logic function in a greybox or early prototype context. |
| Alpha | Parameterization logic is linked, the shared gameplay loop is playable end to end, and the MVP scenario can be completed without critical failures. |
| Beta | All Must-Have and Should-Have features are implemented and internally tested, including cluster-based fire simulation, ToolWheel equipment set, and Specialized Squad AI (Extinguish/Rescue/Breach). Both approved scenarios are playable through the shared gameplay architecture. |
| Final | High / critical defects are removed, scoring is balanced, both scenarios are stable in the final build, and the submission package is complete. |

# Verification and Validation Approach

Verification ensures the product is built correctly according to specifications, while validation ensures the product remains suitable for its intended educational use. Because Ignis Guard is a serious game, validation must cover not only software correctness, but also the clarity of the player experience, the usefulness of the debriefing feedback, and the consistency of the intended learning outcomes across both implemented scenarios.

The project therefore applies multiple levels of verification and validation, ranging from logic checks and integration testing to system playtests and educational evaluation. Evidence is collected incrementally throughout development and reviewed at milestone gates to confirm that both the shared systems and the scenario-specific implementations meet the project’s technical and academic expectations.

Table 8.1 Verification Levels and Supporting Test Evidence

| Level / Method | Focus | Examples | Expected Evidence |
| --- | --- | --- | --- |
| Logic / Unit-like checks | Deterministic rule logic | Incident State mapping, scoring calculation, prerequisite rules, IncidentSeedUtility determinism (same seed run 3× must produce identical world state). | Test notes, repeatable outputs, fixed edge-case defects |
| Integration testing | Data transfer between systems and correct application of scenario-specific configuration | Call Phase to scene adaptation, scenario loading to hazard setup, command UI to bot behavior, mission trigger to debrief. | Integration test cases and pass/fail records |
| Playmode / System testing | Playable end-to-end behavior across implemented scenarios | Complete loop from Main Menu / Scenario Start to Result/Debrief for both approved scenarios. | System test checklist, crash log status, build notes |
| Usability and educational evaluation | Clarity, usefulness, perceived learning value, and cross-scenario consistency | Debrief clarity, control intuitiveness, mission pacing, tactical understanding, and perceived difference between scenario conditions. | Evaluation forms, summarized findings, corrective actions |

## Validation Focus Areas

- Functional coverage against SRS-defined core features, system flow, and scenario-loading behavior.

- Non-functional coverage for performance, stability, usability, and documentation readiness across both implemented scenarios.

- Educational validation of debrief usefulness, consequence awareness, and scenario-specific mission clarity.

- Supervisor review of scenario logic, SOP-oriented mission sequencing, and cross-scenario consistency of the shared architecture.

# Configuration, Change, and Risk Control

Configuration and change control protect the project baseline from unplanned drift. Since the project is executed by a small team under a fixed capstone timeline, disciplined change control is essential.

## Configuration Management

- Source code is managed in Git with at least main, develop, and feature branches.

- Executable builds follow semantic-style version naming (for example: v0.5.1_Alpha).

- Jira is the primary task and sprint tracking system.

- Non-code artifacts such as documents, design assets, and meeting notes are stored in shared cloud repositories.

## Change Control

Table 9.1 Steps in the Project Change Management Process

| Step | Purpose | Typical Decision Questions |
| --- | --- | --- |
| Proposal | Register the requested change and explain why it is needed. | What is changing? Why now? |
| Impact Analysis | Assess schedule, technical complexity, educational value, and risk impact. | Will the change delay a sprint or compromise MVP quality? |
| Decision | Approve, defer, simplify, or reject the change. | Is the change aligned with the approved MVP and available time? |
| Implementation and Baseline Update | Execute approved change and update affected documents/backlog. | Which artifacts need revision and who owns them? |
| Communication / Supervisor Notification | Inform the project supervisor of any approved change that affects scope, schedule, or a milestone deliverable. | Does this change affect a milestone, a baseline deliverable, or the approved MoSCoW classification? |

## Risk-Control Rules

- MoSCoW prioritization is the primary control against scope creep.

- After Week 16, the team enters a controlled stabilization phase with no new major features.

- If a delay exceeds one sprint, the team should first simplify Could-Have scope, then reduce the content complexity of the secondary scenario before compromising the shared core gameplay loop. Must-Have features — including Squad AI (Extinguish/Rescue/Breach) — must not be reduced or deferred.

- Risk ownership is reviewed during sprint reviews and milestone checks.

- After the MVP scenario is validated, new work for the second scenario should prioritize reuse of existing systems rather than introducing new standalone mechanics.

# Metrics, Reporting, and Corrective Action

The team monitors both delivery progress and product quality. Metrics are used to identify deviations early and trigger corrective action before they threaten the approved two-scenario delivery baseline.

Table 10.1 Progress Monitoring Reports and Corrective Triggers

| Metric / Report | Purpose | Frequency | Corrective Trigger |
| --- | --- | --- | --- |
| Sprint burndown / remaining work | Check whether sprint velocity is sufficient. | Per sprint | Backlog reduction, task re-assignment, or scope cut |
| Feature completion checklist | Track status against Must / Should / Could priorities. | Continuous | Escalate blocked features, protect the MVP scenario baseline, and reduce secondary-scenario complexity if required |
| Bug count by severity | Track product stability and testing load. | Continuous during QA | Fix critical/high items before milestone sign-off |
| Playtest notes | Capture usability and educational issues. | During internal and user tests | UI/content/debrief adjustments |
| Weekly status sync | Report Done / Next / Blockers to maintain control. | Weekly | Immediate blocker resolution |
| Sprint review report | Summarize completed sprint goal and risk status. | Every 2 weeks | Re-plan next sprint if goals were missed |
| Milestone review | Evaluate readiness at major gates. | At each quality gate (Prototype / Alpha / Beta / Final) | No gate pass until acceptance criteria are satisfied |

## Corrective Action Policy

When quality or schedule indicators fall outside acceptable limits, the team must record the issue, assign an owner, define a corrective action, and verify the result in the next review cycle. Corrective action may include scope reduction, defect triage, process adjustment, additional regression testing, or revision of unclear content/specification artifacts.

# Conclusion

This Software Process and Quality Plan provides a focused governance framework for Ignis Guard. It translates the guidebook’s expectations for process, roles, activities, deliverables, and quality control into a practical capstone process for a serious game developed through a shared gameplay architecture and two playable scenarios.

By separating this document from the Project Plan, the team gains a clearer place to maintain process rules, quality objectives, verification discipline, and corrective action policies without overloading schedule-oriented planning sections. The resulting process model supports iterative development, controlled scope management, documentation traceability, and milestone-based quality review.

The plan also reflects the project’s updated implementation strategy: one scenario is treated as the MVP validation baseline, while the second scenario extends the same architecture to demonstrate reuse, consistency, and scalability. This allows the team to preserve feasibility while still validating the educational and technical value of the overall system.

Overall, this document serves as the operational baseline for how Ignis Guard will be developed, reviewed, tested, and improved from initiation through final delivery.